## Tasks
JAAL 1.1 for Dijkstra’s algorithm

Target	Priority	Description	Done	Comment
Schema	1	Add key-value type reference to node	05.10.21
Schema	1	Add key-value type reference to graph		Prevent overgeneralization and discard this for now.
Schema	1	Add key-value type reference to matrix	05.10.21	Already implemented: a matrix contains nodes which may contain key-value pairs. Complex enough for now.
Schema	2	remove attributeList	05.10.21
Schema	3	Event schema: click, grade, undo events	05.10.21
Schema	4	Definitions schema	05.10.21
Schema	5	initialState schema	05.10.21
Schema	6	Animation schema
Schema	7	TimeStamp schema	05.10.21	Inside event schema
Schema	8	Test data: Dijkstra exercise recording (semantics only)
Recorder	9	Update metadata
Recorder	10	Update definitions
Recorder	11	Update initialState
Recorder	12	Update animation
Player	13	Update metadata
Player	14	Update definitions
Player	15	Update initialState
Player	16	Update animation
Jaal Player-Recorder with A+ LMS	17	Integration testing
Schema	50	Schema for SVG data (for each step in student’s and model solution)
Recorder	51	Saving SVG data
Player	52	Playing SVG data

## Schedule
Schedule
	Week
	39	40	41	42	43	44	45	46	47	48
					Hard deadline: DSA Y Graph rounds opens on Tuesday!
Schema	x	x
Recorder			x	x	x	x
Player			x	x	x	x
Integration					x	x	x	x