## Taulukko1
		JAAL & JSAV Player-Recorder requirements
							Legend: 0: missing, 1: partial, 2: ready
Proposal date	No	Category	What we should have?	Who benefits and why?	Priority (1 = highest, 5 = lowest)	Comment	Mariani’s evaluation 27.4.2020	Evaluation 2021	Related requirement	JAAL 1.1 JSON Schema
27.4.2020	11	Functional/JAAL	All relevant exercise data is recorded in JAAL.	Dijkstra’s algorithm: in one third of the submissions the choice of edges is not saved. Also not all CSS is saved for the Dijkstra exercise. The recording contains a mix of SVG and HTML, because JSAV produces that. See also requirement 56.	1	Regarding Dijkstra’s algorithm, this might be related to JSAV or browser.	2	1
18.3.2021	59	Qualitative/Portability	There should be a specification [in JSON Schema] for the algorithm animation language which is independent of the Recorder.	Developer likes that the only detailed specification of the language is NOT the reference implementation.	1	Specification as JSON schema helps data validation and thus reduces software risk.
16.4.2021	73	Functional/JAAL	Graph algorithm exercises should save the order of chosen nodes and edges.		1	Dijkstra’s algorithm exercise must save the order of chosen edges; order of vertices is ambiguous.			72
4.2.2021	54	Functional/JAAL	Minimize the number of keywords in the language: represent visualizable data structures with generic data structures, such as graph and matrix.	Developers and researchers like that the language is general-purpose and not bound to JSAV/OpenDSA.	2	Matrix had this; see Ari’s PhD thesis. The current structure is not very extensible regarding Red-Black Tree, Finger Tree, or Fibonacci Heap. However, Matrix had problems when everything was implemented by class inheritance. Discussions 11.2., 18.3., and 15.4.2021.			64, 66, 67, 68
4.2.2021	55	Qualitative/Portability	Design a general-purpose language which is not bound to OpenDSA/JSAV.	Developers and researchers like that the language is general-purpose and not bound to JSAV/OpenDSA. Furthermore, if JAAL is bound to JSAV, and one of them is changed, also the other needs to be changed to keep things working.	2	JSAV and OpenDSA will become outdated somewhere in the future. JSAV/OpenDSA papers are from 2013-2016, and therefore not very interesting. See also 18.3.2021.
10.2.2021	56	Functional/Portability	Save vector graphics in one standard format, e.g. SVG	The developer likes when they don’t need to write visualization code based on semantic representation. Student and instructor like that the graphics of the exercise can be reproduced accurately.	2	The graphics is also a backup of the semantic data, which increases fault tolerance. (Discussion 18.3.2021)			57
10.2.2021	57	Qualitative/Performance-Efficiency	The recording is compact, containing no redundant data.	The developer, researcher, and LMS administrator like that the data is compact.	2	Currently a Dijkstra recording takes one megabyte, which is too much.			56,58
11.2.2021	66	Functional/JAAL	Edges should have the following information: tag (e.g. name, weight), direction, data element in the beginning and end.		2	Discussions 11.2. and 18.3.2021.			54
11.2.2021	67	Functional/JAAL	In case of two-directional, circular linked list, it should be noted that the layout is linear, horizonal, and the nodes are represented from left to right		2	Discussions 11.2. and 18.3.2021.			54
15.4.2021	68	Functional/JAAL	Nodes should have a legend.		3	Discussion 15.4.2021.			54	node.legend
15.4.2021	69	Functional/JAAL	In the semantic representation, each data structure could have a reference to another data structure, including the contents of the nodes. Example: B-tree should be saved semantically so that the node has a reference to an array which has the keys.		2	Discussion 15.4.2021.			54	node.key
15.4.2021	70	Functional/JAAL	Key-value pairs in the semantic representation have a value under each key.	Developers because of generalizability.	2	XAAL had this. This is different than having separate lists of keys and values concerning B-tree. Discussion 15.4.2021			54
16.4.2021	71	Functional/JAAL	The start node of a graph algorithm must be coded semantically.	Researcher, as this allow more flexible automatic data analysis: it is not needed to assume that the start node is always the first node of the graph.	2	Case Dijkstra’s algorithm: how to code semantically the start node? It is not a proprty of the data structure (graph) but the exercise instruction. Metadata.definitions? In the Dijkstra’s algorithm JSAV exercise this is the node that is colored yellow in the beginning. Discussion 16.4.2021
16.4.2021	72	Functional/JAAL	There should be semantic color coding with e.g. structure-property structure.	Researcher, instructor, student: the ability to view correctly a recording to an exercise where color coding is important.	2	Quicksort JSAV exercise has this: selected/not selected element, pivot, sorted and unsorted element, inside the range of the currect recursive call versus outside. Discussion 16.4.2021.			73
27.1.2021	52	Functional/JAAL	State transfers of data structures must be saved semantically, at high level, e.g. swap, AVL tree rotation.	A researcher can analyse the data automatically.	3	Matrix had this.
27.1.2021	53	Functional/JAAL	State transfers of data structures must be saved hierarchically. E.g. AVL tree rotation as change of pointers.	Student, Instructor and Researcher can see large-scale logical steps in student’s solution (in the Player application).	3	Matrix had this. Discussion 8.4.2021
18.3.2021	58	Functional/JAAL	Data compression is applied to the whole recording or animation graphics.		3	Discussion 18.3.2021.			56
	62	Functional/JAAL	LMS must sanitize JAAL data: JSON schema conformance, eliminate XSS threat		3				40,59
	63	Functional/JAAL	LMS must sanitize JAAL data: limited SVG content (no JavaScript inside)		3				40
18.3.2021	64	Functional/JAAL	In addition to generic data structures, the semantic data in the recording should allow hints on how the data structure should be represented. E.g. generic data structure represented as a red-black tree, linear structure represeted as an array or as a binary heap.		3	Discussion 18.3.2021.			54,65
16.4.2021	74	Functional/JAAL	Nodes and edges should have a style [similar to CSS style].		3	Currently JAAL in Dijkstra’s algorithm exercise: the choice of edges is chosen (excluding a browser bug). However, there is no semantic notation on how clicking an edge changes the visual appearance of nodes and edges. http://xaal.org/schemas/xaal-graphics.xsd.html#type_style 16.4.2021				node.style
16.4.2021	75	Functional/JAAL	Nodes and edges should have generic attributes, such as ”active”, in addition to exercise-specific attributes.		3	JSAV has this.
10.2.2021	60	Qualitative/Reusability	Grand educational software visualization framework for both visual program simulation and visual algorithm simulation.		5	Vislaamo (UUhistle) oli Java-kaudella. JSVEE ja Kelmu nyt kevyellä ylläpidolla. Arin kokemuksella frameworkit kannattaa kirjoittaa uudelleen 10 vuoden välein.
27.4.2020	1	Functional/User	All the actions that can be performed on a data structure are recorder and replayed in the animation.				1
27.4.2020	2	Functional/User	The animation can be viewed step-by-step as a slideshow.				2
27.4.2020	3	Functional/User	The animation can be viewed using play/pause/stop buttons.				2
27.4.2020	4	Functional/User	All relevant information shown in the exercise is shown also in the animation.				2
27.4.2020	5	Functional/User	Clicking the exercise control buttons is saved and shown in the animation.				1
27.4.2020	6	Functional/User	If the model answer is opened by the user, this is also shown in the animation.				2
27.4.2020	7	Functional/User	The model answer is shown together with the animation, so that the user can compare it to the own solution.				0
27.4.2020	8	Functional/User	It is possible to share animations.				1
27.4.2020	9	Functional/User	It is possible to export & import animations.				0
27.4.2020	10	Functional/JAAL	All relevant GUI actions saved in JAAL.				1
27.4.2020	12	Functional/JAAL	All saved submissions are available in the JAAL format.				1
27.4.2020	13	Functional/JAAL	The application can be connected to a LMS.				0
27.4.2020	14	Functional/JAAL	The JAAL object is sent to the LMS when the user clicks the grade and reset buttons, and reloads or closes the window.				1
27.4.2020	15	Functional/JAAL	The model answer is saved in JAAL.				0
27.4.2020	16	Functional/JAAL	The JAAL object contains the application and language version.	Developer, as the structure of the language might be radicaly changed if the other requirements change.	1		0		51
27.4.2020	17	Qualitative/Functional-Suitability	The functionalities specified by the requirements are present.				1
27.4.2020	18	Qualitative/Functional-Suitability	The functionalities specified by the requirements work with a satisfactory degree of precision.				2
27.4.2020	19	Qualitative/Functional-Suitability	The functionalities specified by the requirements are presented in an appropriate and understandable way, avoiding unnecessary steps.				2
27.4.2020	20	Qualitative/Performance-Efficiency	The recording of the VAS exercise does not slow down the execution of the exercise steps.				2
27.4.2020	21	Qualitative/Performance-Efficiency	The creation of the animation does not require noticeable loading time.				2
27.4.2020	22	Qualitative/Performance-Efficiency	The resources used by the application have to be reasonable in relation to its functionalities.				2
27.4.2020	23	Qualitative/Performance-Efficiency	The amount of sessions is not limited.				2
27.4.2020	24	Qualitative/Performance-Efficiency	For each exercise session is possible to record one exercise.				2
27.4.2020	25	Qualitative/Performance-Efficiency	For each animation session is possible to play one animation at time.				2
27.4.2020	26	Qualitative/Compatibility	The application works in conjunction with JSAV and its required libraries.				1
27.4.2020	27	Qualitative/Compatibility	The application works when embedded in the Learning Management System.			Integration to A+ LMS was done in summer-autumn 2020.	1	2
27.4.2020	28	Qualitative/Compatibility	The application is able to exchange the required information with the LMS.				1
27.4.2020	29	Qualitative/Usability	The application users find it useful when used according to the given use cases.				1
27.4.2020	30	Qualitative/Usability	It is easy to learn how to use the application.				1
27.4.2020	31	Qualitative/Usability	The application is easy to use and control.				1
27.4.2020	32	Qualitative/Usability	The application protects the user from making errors when recording the exercise or playing the animation.				1
27.4.2020	33	Qualitative/Usability	The user interface enables pleasing and satisfying interaction for the user.	Students, especially those requiring high constrast or large font size.		Custom	1
27.4.2020	34	Qualitative/Usability	The application is usable also by people with diverse abilities.			Target: the same accessibility level than A+ in general. Challenge: JSAV must be modified. https://www.w3.org/TR/WCAG20/	1
27.4.2020	35	Qualitative/Reliability	The application is reliable under normal conditions.				2
27.4.2020	36	Qualitative/Reliability	The application is available and accessible when required for use.				1
27.4.2020	37	Qualitative/Reliability	The application works as intended even when an error occurs.				1
27.4.2020	38	Qualitative/Reliability	The application recovers in case of failure or interruption without losing he data.				N/A
27.4.2020	39	Qualitative/Security	The data is accessible only to those who are authorized to have access.				LMS
27.4.2020	40	Qualitative/Security	The application prevents unauthorized access and modification of data.	Everyone		Unrestricted HTML and SVG allow cross-site scripting. Ideally, the LMS should validate the data before storage. The Player should also validate the recording before loading it.	LMS, Player	0
27.4.2020	41	Qualitative/Security	The application records relevant user interaction.				LMS
27.4.2020	42	Qualitative/Security	The recorded user interaction is traced to the user.				LMS
27.4.2020	43	Qualitative/Security	The identity of the user whose interaction has been recorded can be proven.				LMS
27.4.2020	44	Qualitative/Maintainability	The application is designed of modules, such that change to one of them has minimal impact to other modules.				2
27.4.2020	45	Qualitative/Maintainability	The modules composing the application can be easily reused in other software.				1
27.4.2020	46	Qualitative/Maintainability	The application is designed and written in a way, that analyzing it is not too difficult. For example to asses the impact of some changes, or diagnose the cause of a failure.				1
27.4.2020	47	Qualitative/Maintainability	The application can be effectively and efficiently modified without degrading its quality.				1
27.4.2020	48	Qualitative/Maintainability	Test criteria are established for the application, and tests can be performed to verify if the criteria are met.				1
27.4.2020	49	Qualitative/Portability	The application can be adapted for use on different environments. For example different LMSs.			Integration to A+ LMS was done in summer-autumn 2020.	2	2
27.4.2020	50	Qualitative/Portability	The application can be deployed in the needed environment efficiently and with effectiveness.				2
27.4.2020	51	Qualitative/Portability	The application can easily be replaced with new versions of the same application or other similar applications.				2
18.3.2021	65	Functional/JAAL	The recording should contain an actual implementation of the data structure.	(Is this really relevant for an algorithm animation language? -Artturi)		There are unlimited number of implementations for an arbitrary data structure. (Discussion 18.3.2021)			64
	76
	77
	78
	79
	80
	81
	82
	83
	84
	85
	86
	87
	88
	89
	90
	91
	92
	93
	94
	95
	96
	97
	98
	99
	100
	101
	102
	103
	104